## Agile Scrum Gantt
🐄 Maveshi Care AI – Agile Scrum Gantt Chart ¦ 16 Sprints × 2 Weeks = 32 Weeks (8 Months)
Riphah International University ¦ Supervisor: Ms. Uzma Kiran ¦ BSSE 2026 ¦ Methodology: Agile Scrum (Sprint Planning → Daily Standup → Sprint Review → Retrospective)
|  |  |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16
◆ MILESTONES |  |  |  | Sprint 3: ◆ M1 Proposal; Sprint 9: ◆ M2 SRS Done |  |  |  | ◆ M3 Dev Done |  | ◆ M4 Testing | ◆ M5 Final Sub
# | Task / User Story | Owner | Category | S1 Wk 1-2 | S2 Wk 3-4 | S3 Wk 5-6 | S4 Wk 7-8 | S5 Wk 9-10 | S6 Wk 11-12 | S7 Wk 13-14 | S8 Wk 15-16 | S9 Wk 17-18 | S10 Wk 19-20 | S11 Wk 21-22 | S12 Wk 23-24 | S13 Wk 25-26 | S14 Wk 27-28 | S15 Wk 29-30 | S16 Wk 31-32
▸ PROJECT MANAGEMENT
1 | Idea Selection & Proposal | All Members | Project Mgmt | bar: Sprint 1
2 | Write Proposal | Awais | Project Mgmt | bar: Sprint 1 to Sprint 2
3 | WBS & Project Planning | Gulraiz + Wahib | Project Mgmt | bar: Sprint 2 to Sprint 3
▸ DOCUMENTATION
4 | Requirement Study / SRS | Gulraiz + Wahib | Documentation | bar: Sprint 4 to Sprint 6
5 | Literature Review | Gulraiz + Awais | Documentation | bar: Sprint 5 to Sprint 7
6 | UML Diagrams | Awais | Documentation | bar: Sprint 5 to Sprint 7
7 | Final SRS Documentation | Gulraiz | Documentation | bar: Sprint 8 to Sprint 9
▸ DEVELOPMENT
8 | Backend Setup & DB Design | All Members | Development | [9 empty] | █ | █ | █ | █
9 | AI Model (CNN/ResNet50) | Gulraiz | Development | [9 empty] | █ | █ | █ | █
10 | Farmer Mobile App | Gulraiz + Awais | Development | [10 empty] | █ | █ | █
11 | Vet Telemedicine Dashboard | Gulraiz + Awais | Development | [10 empty] | █ | █ | █
12 | Admin Panel | Wahib | Development | [9 empty] | █ | █ | █ | █
13 | AI Chatbot (Urdu/Punjabi) | Gulraiz | Development | [10 empty] | █ | █ | █
14 | Medicine Marketplace | Awais + Wahib | Development | [10 empty] | █ | █ | █
15 | Cloud Deployment (AWS/Azure) | Awais + Wahib | Development | [11 empty] | █ | █
▸ TESTING
16 | Unit Testing | All Members | Testing | [13 empty] | █ | █
17 | Integration Testing | All Members | Testing | [13 empty] | █ | █
18 | Security Testing | Wahib | Testing | [13 empty] | █ | █
19 | UAT & Bug Fixes | All Members | Testing | [13 empty] | █ | █
▸ FINAL SUBMISSION
20 | Final Report Writing | All Members | Final Submission | [15 empty] | █
21 | Presentation Preparation | All Members | Final Submission | [15 empty] | █
LEGEND |  |  |  | ■ | Project Mgmt |  | ■ | Documentation |  | ■ | Development |  | ■ | Testing |  | ■ | Final Submission |  | ◆ Milestone
SCRUM CEREMONIES |  |  |  | 📋 Sprint Planning | 🏃 Daily Standup | 🔍 Sprint Review | 🔄 Retro- spective | 📋 Sprint Planning | 🏃 Daily Standup | 🔍 Sprint Review | 🔄 Retro- spective | 📋 Sprint Planning | 🏃 Daily Standup | 🔍 Sprint Review | 🔄 Retro- spective | 📋 Sprint Planning | 🏃 Daily Standup | 🔍 Sprint Review | 🔄 Retro- spective